# 29.	Education Project – Progress Report

| - Contact Name and Details | The Revd David Gamble Email: education@methodistchurch.org.uk |
| --- | --- |

Introduction

The 2012 Conference adopted eight resolutions relating to the Education Commission’s Report and its Recommendations. Some Recommendations were dealt with immediately by the Conference itself, while others were referred to various bodies, including the Methodist Council. (Resolution 24/7(2012)),   The Council was instructed to consider those proposals, take any action that it deemed appropriate, and report on such consideration and action to the Conference of 2013.

The Commission had recommended (Recommendation 14) subject to funding being available, a two year ‘transitionary project’ to deal with much of what was referred to the Council. Funding was made available by the Connexional Grants Committee and the Revd David Gamble was appointed to the post of Education Project Officer on 26 September 2013.

The Project Officer is responsible to a Steering Group chaired by the Revd Dr John Barrett (Chair of the Education Commission), along with the Head of Discipleship and Ministries (Jude Levermore) and the Revd Dr David Deeks (the Chair of The Methodist Independent Schools Trust (MIST) and the Methodist Academies and Schools Trust (MAST)). At a later stage it was agreed to add a Chair of District to the Group. The Revd Stephen Burgess, Chair of the York and Hull District, was appointed by the Chairs Meeting.

The project has responsibilities, either explicit or implicit, relating to some but not all of the Commission’s Recommendations. Five were explicitly linked to the project. Three others were directed elsewhere, but with implications for the project.  Two were for Districts and Circuits to review in their own context and then report to MIST and MAST by 2014. The project is offering support to the Districts in enabling this to happen, identifying what needs reporting and how, etc. Recommendation 9a was addressed to Methodist independent schools and the project has a role in advocacy and relationship-strengthening. Recommendation 9b related to bringing together the two Methodist educational trusts, MIST and MAST, by 2017 at the latest and work on this has begun.

In April the Methodist Council received an Interim Report of the Education Project, describing progress on the Recommendations for which it and the Project has some responsibility.

Recommendation 1	(Regional gatherings)

The Commission recommended that Districts explore the possibility of annual regional gatherings for Methodist people involved in education to offer advice and support, and the opportunity for networking and personal development. The Project Officer has contacted all Chairs of Districts regarding possible ways forward in response to this recommendation and is currently in discussion with several Districts about setting up regional or District gatherings. We expect to share what we learn from the experience of early gatherings with other Districts.

Recommendation 4	(Educational chaplaincy)

The Conference affirmed and recognised the tremendous opportunities offered by engaging in Education Chaplaincy and affirmed existing plans within the Connexional Team regarding developments in educational chaplaincy. The Steering Group has included matters relating to chaplaincy and churches’ relationships with their local schools (both Methodist schools and community schools) in its contact with all Districts throughout the Connexion.  There is already some very good experience in this area to learn from and share throughout the Connexion. This will remain an important area for development.

Recommendation 8 (Districts to report to MAST on increased number of Methodist schools)

The Commission recommended that the Conference should seek to increase the number of Methodist state-funded schools over the next ten years as opportunity arises, with a priority for areas of socio-economic deprivation. To this end, the Commission recommended that Districts should assess the need and opportunity in their local communities and report to MAST no later than 2014. Such schools should have an ecumenical foundation wherever possible.

The Steering Group has contacted all the English Districts regarding this recommendation, suggesting how to respond to it and report back to MAST. There are already discussions taking place regarding a number of likely new schools.  Work is being done (see below, Recommendation 9) to ensure that the Methodist Church is able to respond to appropriate opportunities as they arise. On 20 March a meeting of District Schools’ Officers was held, to explore what further support such Officers need to help them respond to local opportunities. Not all Districts have such Officers, and the Project Officer has met with District Chairs to discuss how to recruit – and subsequently support - people with the right expertise and experience for this significant role.

Recommendation 9 (Affirmation of MIST, encouragement of participation of independent schools, merger of MIST and MAST within five years)

The Conference (Resolution 24/4(2012)) urged all Methodist independent schools to participate in the continuing development of MIST and the Project is working to encourage this.

The Conference (Resolution 24/5(2012)) directed MIST and MAST to work together wherever possible with a view to becoming a single trust no later than 2017. Already the Connexional Team and MIST staff are working on particular matters and the Steering Group has seconded two Heads from Methodist Schools (one MIST and one MAST) part-time for a period of six months (April to October) to oversee and coordinate the work of a small group of staff and accredited volunteers to develop collaborative and flexible ways of working among those staff and volunteers; and to empower this cluster of staff/volunteers to identify, release and coordinate skilled and experienced educational resource people in the Methodist Church to help processes of change.

Some District Schools Officers have already raised the question of whether and how they relate to MIST schools in their District (which has not generally happened in the past). The Project Steering Group believes District Schools Officers should relate to both MAST and MIST schools.

In addition, a meeting of representatives of both trust bodies is envisaged within the next few months.

Thought is currently being given, in consultation with members of the Law and Polity Committee, to possible models for eventually bringing the Trusts together. This group of people is also considering what amendments to Standing Orders will be needed.

Recommendation 10	(Review and report of District/Circuit engagement with MIST and MAST schools)

The Commission recommended that Districts and Circuits review their engagement with Methodist schools and those who work in them, reporting to MIST/MAST no later than June 2014. The Steering Group has contacted the Wales Synod and the 21 English Districts in which there are currently Methodist or joint schools regarding their response.

Recommendation 11	(Senior educational post)

The Commission recommended that a senior officer within the Connexional Team be appointed to take responsibility for overseeing all of the Methodist Church’s involvement in formal education. Consideration is being given to precisely what shape such a post will take.

Recommendation 12    (Appointment of Education Forum)

The Commission recommended that an Education Forum be appointed to advise and assist officers of the Connexional Team in respect of educational policies and practices. The Steering Group has already made progress on this and agreed to the setting up of a Forum made up as follows:

Chair – Senior Education Officer (when appointed. In the meantime, the Project Officer)

Secretary – a member of the Education staff

Chair of MIST and MAST

2 Representatives of MAST – one officer and one serving Head

2 Representatives of MIST – one officer and one serving Head

1 Representative of Chaplaincy to education

1 Representative of Higher Education

1 Representative of Further Education

1 District Chair

1 Representative of the Connexional Team

Representatives for the Forum are currently being identified by those responsible for doing so and the Forum’s first meeting is scheduled for June or July of this connexional year. Consideration is being given to appropriate ways in which the student ‘voice’ can be included.

Recommendation 13 	(Budget provision)

In the early stages of joint working between the staffs of MIST and MAST and responding to requests for involvement relating to possible new schools or conversions to academies, consideration is being given to how to assess the opportunities, different possible ways of working, precisely what staffing and other resources would be required and what would be the budgetary implications.

***RESOLUTION

29/1.	The Conference received the report.